## Page 1
Number | Opened | Contact | IBM Accounts | Short description | Current Status / Next Steps | Severity | State | Status | CIR Requested | Category | Assignment group | Assigned to | Updated
CS1997650 | 2020-10-03 17:00 | MANI AMATCHIAR SUBRA | CT-American Airlines | US South Connectivity issues | 12/2 - Hello Mani, Thank you for reaching out.So no errors today? Or is it still occuring? Please do confirm, if so can you re run the debug tool and attach the results to this case please. Thank you! 12/2 - Yesterday there were 400 errors around 1st Dec 10 PM CST. Yes, there were few errors until before that day. 12/2 - Hello Mani, Thank you for reaching out.So no errors today? Or is it still occuring? Please do confirm, if so can you re run the debug tool and attach the results to this case please. Thank you! | Sev - 2 | In Progress | New | FALSE | Infrastructure | acs-fabric | Javed Iqbal Abdul | 2020-12-02 16:38
CS2048075 | 2020-11-10 09:33 | Franco Guidoli | CT-American Airlines | CoreDNS Connectivity problems | 12/3 - Close notes: Solution provided by IBM support engineer 12/1 - Hello Franco The container team has investigate the issue. They looked at both of these cluster masters, and could not find anything that corresponded directly to the times mentioned by your. However the connections from the worker to the customer master go through the control plane NodePorts, which could go through any of the control plane workers. So if the worker the connection was going through was rebooted (to apply security patches, etc), that would explain the connection interruption between coreDNS pod and master, and will not cause DNS lookup failures. In order to investigate this further, we will need your to provide more information which can show evidence that "coredns failures are triggering DNS failures in application pods which is evident from the screenshots attached". Container team looked at the screenshots that are attached, but don't see any evidence of DNS lookup failures. Based on the screenshot they can see your monitoring is just showing that the coreDNS pods are showing an occasional error, which is normal and expected, and will not cause a problem. Thanks for your understanding. Please let us know for any questions. | Sev - 2 | Resolved | New | FALSE | Services | acs-fabric | John Frick | 2020-12-01 23:59
CS2057390 | 2020-11-17 11:33 | Ray Hudaihed | Legacy CorpTech account | Needs a support person to help force a master changeover | 12/3 - Requested swtich overs completed by IBM today (4). Per Ray, The dev team is making changes and they'll need to a changeover to occur on 12/09 (@ 8am, 9am, 10am & 11am CST). I'll update this ticket the day before as a reminder. 12/2 - Hello Ray We will again put this on the list for tomorrow morning and update as needed. | Sev - 2 | In Progress | New | FALSE | Services | WDP Compose Support | Frank Isaacs | 2020-12-02 12:32
CS2076185 | 2020-12-02 09:00 | Larry Spence | CT-American Airlines | Web Platform: AACOM DB - PROD IBM Postgresql db replication is down on WDC repl 1 and 2 - 12-2-2020 3:47 AM CST AM | 12/3 - ETA for fix is mid week ending 12/11/20 12/2 - Hi, Larry - Regarding the query you're running, at that point, the replica is not connected to the primary, so pg_stat_replication on the primary will not show it. You'll need to monitor the replication status from the replicas themselves if you are looking for real-time information while the replica is catching up from COS. Obviously the underlying issue is different than this, and we'll certainly update the case as requested. | Sev - 2 | In Progress | New | FALSE | Services | WDP Compose Support | Frank Isaacs | 2020-12-02 12:28
CS2051098 | 2020-11-12 13:49 | Chandrajeet Patil | Revenue Management | Monitoring Alert: kube-br3uinmd0ss5supdmq10-rfdbprodclu-default-0003105d.iks.ibm | 12/3 - TAM escalating on behalf of AA to obtain a status for the fix 12/1 - Hi Chandrajeet, No estimate on ETA from the dev team, and it is still active on Jira. I am assuming the recent holidays delayed the implementation of the fix. Please let me know if you have any questions. | Sev - 2 | In Progress | New | FALSE | Services | acs-fabric | Garrett Stark | 2020-12-01 09:24
CS2047036 | 2020-11-09 14:44 | RODOLFO STEFANINI | CT-American Airlines | Node not restarting or updating | 12/3 - The following update from Rodolfo Stefanini - Today updated workes . master update kept n sync without issues. 1 workernode just ended in a unstable state , solved after the reboot. so i guess we are good with the ticket. Folder permission is been addressed by dynatrace team. This ticket can be closed 12/3 - Support is seeing the workers are all healthy. TAM following up with Rodolfo to confirm he is no longer seeing the issue 11/29 - Hello Rodolfo, Any updates on this issue? Thank you. | Sev - 3 | In Progress | New | FALSE | Services | acs-fabric | Ranjith Rajaram Salem | 2020-11-29 21:26
CS2072699 | 2020-11-30 10:28 | Shannon Callies | Legacy CorpTech account | Issues authenticating app in public CF | 12/1 - Thank you for your update Shannon, Here is the latest update from our internal APP ID team: We found only a single failure for the reported tenant, `2fe596d1-7dcf-4cab-a3b3-b845f2ad7ac2`, in the past few weeks. We noticed a few failures for `GET https://us-south.appid.cloud.ibm.com/oauth/v4/2fe596d1-7dcf-4cab-a3b3-b845f2ad7ac2/token`, probably attempts to hit the endpoint directly using a browser/curl/some HTTP client. The GET method is not supported and not being used as part of the authentication flow, only `POST`. | Sev - 3 | In Progress | New | FALSE | Services | acs-security | Jonathan Sanchez | 2020-12-01 10:11
CS2057324 | 2020-11-17 10:46 | Fredric Cohen | Revenue Management | Node provision failures in dal13 zone | 12/3 - Hello Fred, Based on your Slack with Jay A, I understand that this has not been a problem since the day you opened the ticket. I will close the ticket, but please let us know if you see the problem again. 12/2 - TAM following up with CSM for update 11/24 - Pending update from assisgned CSM | Sev - 3 | In Progress | New | FALSE | Services | Sales | George Ringel | 2020-11-24 00:03
CS2066673 | 2020-11-24 22:10 | Mani Balasubramanian | Legacy CorpTech account | Stale data on IBM billing usage private endpoint (CSV Extract) for American Airlines | 12/2 - Hello Mani, Thank you for choosing IBM Cloud and reaching out to us for assistance. We are currently performing the initial review and investigation into your request and I will provide you with an update soon. In the meantime, please let me know if you have any additional questions. Kind regards, IBM Cloud support 12/2 - TAM escalating for update from IBM RSET team 11/24 - Pending udpate from RSET | Sev - 3 | In Progress | In Progress | FALSE | Project Office | Bluemix RSET | Daffney Carpenter | 2020-11-26 08:14
CS2066111 | 2020-11-24 11:52 | Opiee Vajinapalli | CT-American Airlines | Web Platform: AACOM DB - Prod - Not seeing pgbackres messages in log lines in rep1 and rep2 after master db restarted at 245am nov 24 2020 | 12/1 - Great - do you need anything else on this case, then, or can we mark it resolved? Thanks - 12/1 - oh okay, good then we can do silent test on our services and see all critical functions are working fine. tq for the update. 11/30 - Hi, Opiee - it looks like that code update was merged and released last week. There isn't another one scheduled for this week that I know of. Please let us know if you have further questions! | Sev - 3 | In Progress | New | FALSE | Services | WDP Compose Support | Frank Isaacs | 2020-12-02 08:32
CS2066666 | 2020-11-24 22:04 | Mani Balasubramanian | Legacy CorpTech account | Empty HTTP response on IBM billing usage private endpoint (CSV Extract) for American Airlines | 11/24 - Hello Mani, Thank you for choosing IBM Cloud and reaching out to us for assistance. We are currently performing the initial review and investigation into your request and I will provide you with an update soon. In the meantime, please let me know if you have any additional questions. Kind regards, | Sev - 3 | In Progress | In Progress | FALSE | Project Office | Bluemix RSET | Daffney Carpenter | 2020-11-26 08:14
CS2064985 | 2020-11-23 14:26 | Techinf BMX | ETS - American Airlines | Not all domains are listed in CF Org | 12/1 - Techinf BMX Team, Thank you for your patience as we work on this. We're looking into a pagination issue that may be causing this issue. Would it be possible to get a list of the domains that are missing so that we can match them against the list in the API call that we're seeing on the back-end? | Sev - 4 | In Progress | New | FALSE | Project Office | acs-fabric | Joe Mclemore | 2020-12-01 11:49
CS2074576 | 2020-12-01 11:07 | CHRISTOPHER LANGSTON | Legacy CorpTech account | Listing COS Objects Gets Stuck Using Web Portal | 12/1 - Hello Christopher, I have observed list objects at portal UI is spinning endless when browser cache is corrupt. Would you please try it again after clear browser cache/cookie? 12/1 - Hi Bryan, Try reproducing the issue using Chrome. As for the other browser, Firefox works, IE11 is not supported and there's a configuration issue with our SSO when using Edge so I couldn't test that. I prefer using the S3 Browser, however, it has an issue when going through our network but works fine when I connect from outside the AA network. Best Regards, | Sev - 4 | In Progress | New | FALSE | Services | acs-storage | Bryan Schichtel | 2020-12-01 16:12
CS2073489 | 2020-12-01 00:38 | AA-Customer Technology | CT-American Airlines | Emergency VSI Host Evacuation | 12/3 - TAM has reached out to Satish Nallamilli for assistance 12/1 - Dear IBM Cloud Customer, This ticket is being opened to inform you of an issue with the host server your VSI is hosted on. In order to provide a stable environment for your VSI, we are initiating an emergency host evacuation for all VSI's that currently reside on this host. This will relocate your VSI to a more stable host. Once the evacuation has been completed your VSI will be brought back online in a fully functional state. We apologize for any inconvenience this will cause you. Please let us know if you have any questions or if there is anything we can do to assist you moving forward. Thank you, | Sev - 4 | In Progress | New | FALSE | Infrastructure | sl-compute-sre |  | 2020-12-01 00:38
CS1872791 | 2020-07-01 06:18 | AA-Customer Technology | American Airlines | Colocation Service Request | No action required by AA | Sev - 4 | In Progress | In Progress | FALSE | Infrastructure | Sales | Raymond Perreault | 2020-08-25 18:18
CS1872792 | 2020-07-01 06:18 | AA-Customer Technology | American Airlines | Colocation Service Request | No action required by AA | Sev - 4 | In Progress | In Progress | FALSE | Infrastructure | Sales | Raymond Perreault | 2020-08-25 18:17