## Case Review
Number | Opened | Contact | IBM Accounts | Short description | Status / Next Steps | Severity | State | Status | CIR Requested | Category | Assignment group | Assigned to | Updated
CS2038919 | 2020-11-03 09:59 | Larry Spence | CT-American Airlines | Web Platform: AACOM DB - PROD IBM Postgresql db replication is down on WDC repl 1 and 2 - 11-3-2020 1:10AM | 11/5 - Duplicate of CS2005149 | Sev - 2 | In Progress | New | FALSE | Services | WDP Compose Support | Frank Isaacs | 2020-11-03 12:24
CS2036171 | 2020-11-01 16:14 | LUIS PINA GUIZAR | CT-American Airlines | Database degradation | 11/2 - BE team reviewed last two days of statistics in sysdig, saw only 50% memory usage and minimal disk IOPS %. Believe any slowness is likely going to be related to database structure or query design. 11/2 - Anup clarified AA is not encountering any issues now. The ask is understand cause | Sev - 2 | In Progress | New | FALSE | Services | WDP Compose Support | Frank Isaacs | 2020-11-02 14:24
CS1997650 | 2020-10-03 17:00 | MANI AMATCHIAR SUBRA | CT-American Airlines | US South Connectivity issues | 11/2 - Support requesting update - Did AA maked the expected changes on their end to see if their behavior/issue improved 10/12 - Webhook configured on the AA side as requested but needed to be turned off as it was spamming the Slack channel; AA will advise Support if the issue reoccurs 10/6 - Jay provided instructions for creating the webhook 10/5 - Support created a Webhook which will notify IBM when a connectivity issue occurs again 10/3 - While trouble shooting related case CS1986797, which was for US EastCase, this case was opened on behalf of AA to investigate the connectivity issues in US South Impacted ClusterId: loyalty-upgrades-prod-dal/bsuo5o7d08mit2ajo7ng NAME STATUS ROLES AGE VERSION INTERNAL-IP EXTERNAL-IP OS-IMAGE KERNEL-VERSION CONTAINER-RUNTIME 10.176.252.3 Ready <none> 45d v1.17.11+IKS 10.176.252.3 150.239.23.79 Ubuntu 18.04.5 LTS 4.15.0-112-generic containerd://1.3.4 10.176.252.77 Ready <none> 45d v1.17.11+IKS 10.176.252.77 150.239.23.67 Ubuntu 18.04.5 LTS 4.15.0-112-generic containerd://1.3.4 10.241.70.179 Ready <none> 45d v1.17.11+IKS 10.241.70.179 169.61.189.100 Ubuntu 18.04.5 LTS 4.15.0-112-generic containerd://1.3.4 10.241.70.248 Ready <none> 45d v1.17.11+IKS 10.241.70.248 169.48.253.164 Ubuntu 18.04.5 LTS 4.15.0-112-generic containerd://1.3.4 IBM Support was unable to replicate the connectivity issues. Waiting on response from AA - Is AA still seeing the issue; Is AA able to replicate the issue? | Sev - 2 | In Progress | New | FALSE | Infrastructure | acs-network | Shibu Melodan | 2020-11-02 16:53
CS2024661 | 2020-10-22 15:42 | Manuel Flores Cacho | CT-American Airlines | VCAP Services are not being picked up by out gateway application | 11/4 - Support is requesting additional information - Have you attempted to use this in your application? Do you have a dev or QA environment to test this in? | Sev - 2 | In Progress | New | FALSE | Services | acs-appdev | Kevin Marko | 2020-11-03 10:23
CS2005149 | 2020-10-09 00:04 | Opiee Vajinapalli | CT-American Airlines | Web Platform: AACOM DB - Prod Rep 1 - after resynch effort at 430pm failed to complete after refreshing data in db and shown error to notify IBM Support | 10/27 - Support continuing to investigate the resync issue; Support suspects there is a bug and will work on the fix 10/20 - With regard to CS2005149 and CS2005095, we determined that were bugs in our operational documentation and tooling that was resulting in the source and replica relationship being severed. The team is working on addressing those issues this week 10/14 - it was because oncall operator ran i pfe --enable on RR which made it to be come a regular PG formation with a single member 10/11 - Rep 1 issue -it was somehow configured as stand alone PG, so when you run 'read-replica-resync' the Error response from server. Status code: 422; message was returned; IBM SRE reconfigured the instance as Readonly Replica, which resolved the issue | Sev - 2 | In Progress | New | FALSE | Services | WDP Compose Support | Frank Isaacs | 2020-10-30 06:26
CS2037429 | 2020-11-02 10:39 | Raviteja Tatineni | CT-American Airlines | 403 Forbidden error in Washington region | 11/5 - Support following up for status 11/3 - BE team reveiwed and confirmed that 403 Forbidden error was very unlikely to be caused by network since the response was well received by the app, otherwise it wouldn't log the 403 code. Did AA change any configuration or external service credentials recently? | Sev - 2 | In Progress | New | FALSE | Services | acs-fabric | Sameh Kamel | 2020-11-03 12:24
CS2001876 | 2020-10-07 13:48 | Michael Calabrese | Legacy CorpTech account | Logs not showing consistently within LogDNA | 11/18 - Hello Michael, Thanks for your patience, here is the updates from our tech team: Most of the issues with CF should be resolved, there may still be some timeouts seen which could drop lines less than 1% of the time. We are keeping our internal ticket open to continuously improve on this in the subsequent code refactors. Let us know if you have any updates from the customer. Thank you. | Sev - 3 | In Progress | New | FALSE | Services | acs-appdev | Heda Zhou | 2020-11-01 02:06
CS2032094 | 2020-10-29 09:56 | Shannon Callies | Legacy CorpTech account | Need more detailed notifications for IBM cloud issues | 11/4 - CSM following up with OM | Sev - 3 | In Progress | New | FALSE | Project Office | Bluemix RSET | George Ringel | 2020-10-30 15:11
CS2032149 | 2020-10-29 10:32 | Shannon Callies | Legacy CorpTech account | CF CLI blue-green-deploy plugin issue | 11/4 - Support investigating issue | Sev - 3 | In Progress | New | FALSE | Services | acs-fabric | Sameh Kamel | 2020-11-02 00:48
CS2027599 | 2020-10-26 10:52 | Techinf BMX | ETS - American Airlines | CF ORG - Domains not loading | 11/4 - Support investigating issue | Sev - 3 | In Progress | New | FALSE | Platform | acs-fabric | Joe Mclemore | 2020-11-02 10:41
CS1872791 | 2020-07-01 06:18 | AA-Customer Technology | American Airlines | Colocation Service Request | IBM owned ticket - No action required by AA | Sev - 4 | In Progress | In Progress | FALSE | Infrastructure | Sales | Raymond Perreault | 2020-08-25 18:18
CS1872792 | 2020-07-01 06:18 | AA-Customer Technology | American Airlines | Colocation Service Request | IBM owned ticket - No action required by AA | Sev - 4 | In Progress | In Progress | FALSE | Infrastructure | Sales | Raymond Perreault | 2020-08-25 18:17
CS2034424 | 2020-10-31 04:25 | AA-Customer Technology | CT-American Airlines | Action Required - Host Migration | 11/5 - TAM has requested additional information ie; DC location, Pod and VSI name 11/4 - IBM is requesting AA respond back with a time to perform this maintenance that is most convenient for AA | Sev - 4 | In Progress | New | FALSE | Infrastructure | sl-compute-sre |  | 2020-11-03 10:31
CS2036151 | 2020-11-01 15:00 | Corporate Technology | Revenue Management | Schedule Offline VSI Migration Request | 11/5 - Maintenance will impact VSI located in DAL10 POD 03; The VSI is kube-brsv26bd0pq38hqule90-rfdbdevclus-rfdb 11/4 - IBM is requesting AA respond back with a time to perform this maintenance that is most convenient for AA | Sev - 4 | In Progress | New | FALSE | Infrastructure | sl-compute-sre |  | 2020-11-01 15:03
CS1995502 | 2020-10-01 13:28 | MANI AMATCHIAR SUBRA | CT-American Airlines | 502 Bad gateway Error in IKS | 11/2 - Updated error logs provided for Support review | Sev - 4 | In Progress | New | FALSE | Services | acs-fabric | Javed Iqbal Abdul | 2020-11-03 02:34
CS1999762 | 2020-10-06 02:30 | Opiee Vajinapalli | CT-American Airlines | Web Platform: AACOM DB - Non-prod IBM Postgresql db service QALT replica2 in WDC is out of replication group in Master DB in Dallas | 10/22 - Similarly for QALT environment and DR environment, we are not seeing replicas in master replica set. Awaiting response from Support | Sev - 4 | In Progress | New | FALSE | Services | WDP Compose Support | Frank Isaacs | 2020-10-23 10:07
CS2033476 | 2020-10-30 09:31 | Trijito Santoso | Legacy CorpTech account | Frequent connection lost during Tableau report data refresh to replica DB | 11/3 - Intermittent issue; occurs 50% of the time. IBM investigating | Sev - 4 | In Progress | New | FALSE | Services | WDP Compose Support |  | 2020-10-30 10:53